【Format for Action Plan】

1: Narrative Summary (refer to the attached format)

2: Plan of Operation (refer to the attached format)

3: PPT (10 slides Maximum based on Narrative Summary)

* The action plan should be prepared both in Word-based narrative report and in Power Point-based presentation data.

Action Plan

The J1100711 Group Training Course on

“IMPROVING TEACHING METHODS IN MATHEMATICS IN PRIMARY EDUCATION”

| Name | Angele Jeffrey |
| --- | --- |
| Country | Vanuatu |
| Organization | Lingarak Primary School |
| Position | Head teacher |

| Title | Multiplication |
| --- | --- |
| Period | 6 months |
| Target Location | Lingarak Primary school-Malekula Malampa Province VANUATU |
| Target Group | 5 Primary teachers and 130 students |
| NARRATIVE SUMMARY |  |
| < OVERALL GOAL > |  |
| Children know the meaning, how to construct and apply multiplication with good understanding |  |
| < SPECIFIC OBJECTIVES> (PROJECT PURPOSE) |  |
| The appropriate curriculum sequence and method of teaching multiplying is increasing in lingarak Primary school |  |
| < YOUR LEARNING IN JAPAN> |  |
| - The Configuration of the text book - Introduction-The text book presents the familiar topics to stimulate the pupil’s interest and concern. - Development-The purpose of this component is for all pupils’ to refine their abilities. - Testing-The text book presents Problems for teachers to check the pupils’ understanding. - There are four chapters for multiplication and they are arranged in a meaningful order. - Each chapter has a role in the multiplication learning process - Chapter 1 is about the “MEANING ‘’of multiplication- - Chapter 2 is about LEARNING HOW TO LEARN BY THEMSELVES - Chapter 3 allow the children to APPLY/ADAPT what they learn by themselves - Chapter 4 –Relate what they learn with WORLD (Math World) |  |
| < OUTPUTS by applying your learning in Japan> |  |
| Output: 1 Teacher’s gain good knowledge about the appropriate curriculum sequence. . Output: 2 A textbook is arrange in a meaningful order for each class. |  |
| < ACTIVITIES > |  |
| Output 1< Teacher’s gain good knowledge about the appropriate curriculum sequence Activity 1-1 To conduct a workshop for the teachers to know about the multiplication units in the Japanese text book Output 2< A text book is arrange in a meaningful order for each class. Activity 2-1 To conduct a workshop for the teachers to rearrange Multiplication units in a meaningful order (make a working plan). Activity 2-2 To conduct a meeting to confirm the completion of the text book |  |

Plan of Operation

| Output No. | Activities | Expected results | Time Schedule | Persons in charge |  | Implementers |  | Materials, equipments |  | Budget | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Activity1-1 To conduct a workshop for the teachers to know about the multiplication units in the Japanese text book | --Able to explain the roles of each chapter --Compare the text book with the Vanuatu text book and be convinced to help rearrange the chapters immediate | March |  | Angele Jeffrey |  | Teachers |  | -Questionnaire sheet -Grade 2 vol 1 Japanese math text book --Markers, A3 sheets A4 sheets -Tapes | 5000 Vatu | Easy to start because we do not need fund..I am also in a good position to start the project as planned |
| 2 | Activity2-1 To conduct a workshop for the teachers to rearrange Multiplication units in a meaningful order (make a working plan). Activity 2-2 To conduct a meeting to confirm the completion of the text book | Create a supplementary book for each grade(1-6) for teachers to use in their class rooms Able to use the explain the content of the book and confidently use it | April April-july August |  | Angele Jeffrey Angele Jeffrey Angele Jeffrey |  | Teachers Teachers Teachers |  | -Questionnaire sheet -Grade 2 vol 1 Japanese math text book --Markers, A3 sheets A4 sheets -Tapes |  |  |