Action Plan

28th February 2012

The J1100711 Group Training Course on

“IMPROVING TEACHING METHODS IN MATHEMATICS IN PRIMARY EDUCATION”

| Name | Maboi Zacharia Mphunyane |
| --- | --- |
| Country | Lesotho |
| Organization | Lesotho College of Education |
| Position | Lecturer |

| Title | Establishing structures that will allow use of problem solving approach in mathematics classrooms at Lesotho College of Education. |
| --- | --- |
| Period | 6 months |
| Target Location | Lesotho College of Education |
| Target Group | College Teacher Trainers and 3rd year Students enrolled in mathematics courses. |
| ABBREVIATIONS USED IN THIS NARRATIVE AND IN THE PLAN OF OPERATIONS. LCE-Lesotho College of Education; TTs-Teacher Trainers; LS-Lesson Study; LSG-Lesson Study Group; TT1-Teacher Trainer 1 (Myself). |
| NARRATIVE SUMMARY |  |
| < OVERALL GOAL > |  |
| Students who register for mathematics courses in the LCE pass the courses. |  |
| < SPECIFIC OBJECTIVES> (PROJECT PURPOSE) |  |
| Students at LCE have a positive attitude towards mathematics. |  |
| < YOUR LEARNING IN JAPAN> |  |
| 1.Problem posing: When a question is asked it must usually be in some context. It can refer to a situation related through a story or it can be related by a picture. Problem posing can be developed in students through actually teaching them how to think about writing problem for specific situations. Otherwise problem posing can be used by a teacher to ask questions in a classroom. 2.Problem solving approach to teaching: A method or approach in which the lesson can be based on a given problem. As learners solve the problem they learn a concept. 3.Teaching materials in Japan are made to support teaching through involving learners to learn by-/for themselves. These materials provide a situation that needs learners to think and engage in discussions to explain their thinking. The materials should be either real objects or models of those to allow concretization before conceptualization is done, more especially at elementary level. 4.Textbooks are written in such a way that they are aligned to the flow of a normal classroom lesson, where there is an introductory section, posing of the problem, attempts by learners t solve the problem and explain their thinking , summary by the teacher and then drill to practice the concept. 5. Chalkboard writing is done to ensure all important points remain on the board until the end of the lesson. The structure is also aligned to the flow of the lesson. The introduction is followed by problem posing and the problem is written on the board. Then learners’ thoughts are also reflected on the board followed by their attempts to solve the problem. Then teacher’s summary which also has to be written. |  |
| < OUTPUTS by applying your learning in Japan> |  |
| < ACTIVITIES > |  |
| Output 1 Mathematics TTs vary teaching methods regularly enough depending on the topic and the type of teaching material prepared. Activity 1-1 Invite mathematics TTs to a meeting to brief them about Japan trip and what I have learnt, then introduce lesson study to them. Activity 1-2 To hold a meeting with mathematics TTs to establish a lesson study group in the department. Activity 1-3 To draw guidelines and a schedule for LSG activities. Activity 1-4 To invite views about the concept lesson study from the departments of the Faculty of Education of the Lesotho College of Education. Activity 1-5 To organise and hold periodic consultative meetings between Faculty of Education members responsible over lesson planning, teaching methods and teaching materials and Faculty of Science members who are in the mathematics section to critically look at the use of lesson study as a means to improving teaching at LCE. Activity 1-6 Implement plans to use LS to improve teaching methods of TTs. Output 2 Equipment and appropriate personnel are increased to meet the needs of the students. Activity 2-1. Holds a meeting with Mathematics TTs and discusses proposal to establish a functional mathematics room. Activity 2-2. Prepare and submit a proposal to HOD for allocation of a room to be used as a mathematics room. Activity 2-3. Establishment of a functional mathematics room for storing mathematics equipment and materials. Activity 2-4. Some of the equipment is improvised through projects done by 3rd year mathematics students. Activity 2-5. A proper record of mathematics equipment is prepared and a record book for equipment taken out of the room is also prepared. Output 3 Students use computers for studying and writing assignments in mathematic. Activity 3-1. Prepare and submit a proposal to HOD for trialling the integration of the teaching of some computer skills required for use in some mathematics topics. These include the use of excel for drawing basic graphs and keeping records such as student performance over a period. Activity 3-2. Trialling the integration of the teaching of some computer skills required for use in some mathematics topics. Activity 3-3. Creating d-book for one of the courses offered at LCE. Activity 3-4. Organise team-teaching with staff from the Faculty of Education who are responsible for educational technology on use of d-books and e-boards and other electronically obtained materials. |  |

Plan of Operation:

| Output No. | Activities | Expected results | Time Schedule |  |  |  |  |  |  |  |  |  |  |  |  | Persons in charge | Implementers | Materials, equipments | Budget | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Month (1-Mar; 2 Apr, etc, 6-Aug) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Activity 1-1 Invite mathematics TTs to a meeting to brief them about Japan trip and what TT1 has learnt, then introduce lesson study to them. | TTs attend meeting and give views about lesson study |  | 1 |  |  |  |  |  |  |  |  |  |  | TT1 and HOD |  | TT1, TTs and HOD | Stationery | ¥500 |  |
|  | Activity 1-2 To hold a meeting with TTs to establish a lesson study group in the department. | LSG established |  |  |  |  |  |  |  |  |  |  |  |  | TT1 and HOD |  | TTs and TT1 | Readings and references about LS | ¥1000 |  |
|  | Activity 1-3 To draw guidelines and a schedule for LSG activities. | TTs and TT1 draw guidelines |  |  |  |  |  |  |  |  |  |  |  |  | TT1 |  | TT1, TTs and HOD | Stationery and readings about LSG | ¥1000 |  |
|  | Activity 1-4 To invite views about the concept lesson study from the departments of the Faculty of Education of the Lesotho College of Education. | TTs from other departments give their views about LS |  | 1 |  |  |  |  |  |  |  |  |  |  | HODs |  | HODs and TTs | Questionnaires | ¥500 |  |
|  | Activity 1-5 To organise and hold periodic consultative meetings between Faculty of Education members responsible over lesson planning, teaching methods and teaching materials and Faculty of Science members who are in the mathematics section to critically look at the use of lesson study as a means to improving teaching at LCE. | Meetings held and deliberations made about advantages of holding LS |  | 1 | 2 | 3 | 4 | 5 |  |  |  |  |  |  | TT1 and HOD |  | TTs, HODs and Deans | Stationery | ¥500 |  |
| 2 | Activity 2-1. Hold a meeting with Mathematics TTs and discuss TT1’s proposal to establish a functional Mathematics room. | TTs agree to the proposal and give ideas about how the pace can be run |  | 1 | 2 |  |  |  |  |  |  |  |  |  | TT1 |  | TT1 and HOD | Stationery | ¥500 |  |
|  | Activity 2-2. Prepare and submit a proposal to HOD for allocation of a room to be used as a mathematics room. | HOD’s approval. |  |  | 2 | 3 |  |  |  |  |  |  |  |  | TT1 |  | TT1 | Stationery | ¥50 |  |
|  | Activity 2-3. Establishment of a Functional mathematics room for storing mathematics equipment and materials. | Room allocated. Necessary basic equipment such as shelves installed. |  |  |  |  | 4 | 5 | 6 | S e p t | O c t | N o v |  |  | TT1, TTs, HOD, |  | Dean and Procurement Section of LCE | Equipment to be put in the room such as shelves, tables chairs. | ¥500,000 |  |
|  | Activity 2-4. Some of the equipment is improvised through projects done by 3rd year mathematics students. | 3rd year students donate the materials made from their projects to the mathematics room. |  |  | 2 | 3 | 4 |  |  |  |  |  |  |  | TT1 |  | TT1, students, HOD | N/A | N/A |  |
| 3 | Activity 3-1. Prepare and submit a proposal to HOD for trialling the integration of the teaching of some computer skills required for use in some mathematics topics. These include the use of excel for drawing basic graphs and keeping records such as student performance over a period. | Proposal submitted and HOD approval |  | 1 |  |  |  |  |  |  |  |  |  |  | TT1 |  | TT1 and HOD | Computer software on mathematics applications | ¥50,000 |  |
|  | Activity 3-2. Trialling the integration of the teaching of some computer skills required for use in some mathematics topics. | Trialling done and students’ mixed feelings about the integration observed. |  |  | 2 | 3 |  |  | 6 | S e p t | O c t |  |  |  | TT1 |  | TT1 |  |  |  |
|  | Activity 3-3. Creating d-book for one of the courses offered at LCE. | d-book will simplify reference to textbook, and this will be a point of interest to other TTs. |  | 1 | 2 | 3 | 4 | 5 | 6 |  |  |  |  |  | TT1 |  | TT1 | Hardcopy of a textbook, scanner, pair of scissors, computer and the appropriate software | ¥80,000 |  |
|  | Activity 3-4. Organise team-teaching with staff from the Faculty of Education who are responsible for educational technology on use of e-books and other electronically obtained materials. | Initiate approved by HOD and TTs from those departments |  |  | 2 | 3 | J u n e | J u l y | 6 |  |  |  |  |  | TT1 |  | TT1, HODs of all concerned departments. | N/A | N/A |  |