【Format for Action Plan】

1: Narrative Summary (refer to the attached format)

2: Plan of Operation (refer to the attached format)

3: PPT (Maximum 10 slides based on Narrative Summary)

* The action plan should be prepared both in Word-based narrative report and in Power Point-based presentation data.

Action Plan

The J1100711 Group Training Course on

“IMPROVING TEACHING METHODS IN MATHEMATICS IN PRIMARY EDUCATION”

| Name | Melanie Yangrelbug |
| --- | --- |
| Country | Republic of Palau |
| Organization | Ministry of Education |
| Position | Math Specialist |

| Title | Primary Mathematics Open-Ended Teaching Approach |
| --- | --- |
| Period | Project duration: April 2012 to 2015 |
| Target Location | Ngeremlengui Elementary School |
| Target Group | Grades 1 to 3 |
| NARRATIVE SUMMARY |  |
| < OVERALL GOAL > |  |
| Students master and maintain their grade level math skills and concepts. |  |
| < SPECIFIC OBJECTIVES> (PROJECT PURPOSE) |  |
| Teachers will be able to use open-ended teaching approach. |  |
| < YOUR LEARNING IN JAPAN> |  |
| 1. Problem solving approach 2. 3 Thinking Skills: deductive, inductive, and analogical thinking 3. Blackboard Management 4. Japan Textbook Format 5. Japan Teacher Training Programs |  |
| < OUTPUTS by applying your learning in Japan> |  |
| Output 1 Teachers are able to implement open-ended teaching approach in their class. Output 2 Teachers are able to implement open-ended approach in a lesson-study or open class. |  |
| < ACTIVITIES > |  |
| Output 1 Teachers are able to implement open-ended teaching approach in their class. Activity 1-1 Provide Teacher Training on Open-Ended Teaching Strategies 3 times a year Activity 1-2 Provide Teacher Training on Classroom Management Activity 1-3 Provide Teacher Training on Blackboard Management Output 2 Teachers are able to implement open-ended approach in a lesson-study or open class. Activity 2-1 Develop a lesson study plan using open-ended approach with the pilot school - Guide and assist the teacher in her lesson plan Set up dates for the implementation of her lesson in lesson study Set up a date for implementation of open-ended approach in open class - Monthly Monitoring and Conference - Lesson Study - Open Class |  |

Plan of Operation

| Output No. | Activities | Expected results | Time Schedule (Month of a Year) |  |  |  |  |  |  |  |  |  |  | Persons in charge | Implementers | Materials, equipments | Budget | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Teachers are able to implement open-ended teaching approach in their class. | Activity 1-1 Provide Teacher Training on Open-Ended Teaching Strategies 3 times a year Activity 1-2 Provide Teacher Training on Classroom Management Activity 1-3 Provide Teacher Training on Blackboard Management | . - Overall math grades for each grade on the Quarterly Assessments increased by at least 1.5% every semester. - Math National Average Grade for math students on PAT test increase by at least 2% in a year. | 4 | 5 | 6 | 7 X X X | 8 | 9 | 10 X X X | 11 | 12 | 1 X X X | 2 | Melanie and Chief of Teacher Training | Melanie, Training Specialists, Chief of Teacher Training | Projector, laptop, Japan training documents, transportations | $3,000 | Fund is provided by Federal grants for math programs. |
| 2. Teachers are able to implement open-ended approach in a lesson-study or open class. | Activity 2-1 Teachers apply open-ended approach in lesson study or open class. 2-1-2 Conference with teachers and school principal 2-1-2 Monthly Monitoring 2-1-3 Implementation of open-ended approach in lesson study 2-1-4 Implementation of open-ended approach in open class |  |  |  | X | X | X | X | X X | X X | X | X X | X X | Melanie and Chief of Teacher Training | Melanie, Training Specialists, Chief of Teacher Training, and Pilot School Principal and math teachers | Projector, laptop, Japan training documents, transportation | $100 | (same as above) |