【Format for ActionPlan】

1: Narrative Summary (refer to the attached format)

2: Plan of Operation (refer to the attached format)

3: PPT (Maximum 10 slides based on Narrative Summary)

* The action plan should be prepared both in Word-based narrative report and in Power Point-based presentation data.

Action Plan

The J1100711Group Training Course on

“IMPROVING TEACHING METHODS INMATHEMATICS IN PRIMARY EDUCATION”

| Name | Cherry Oo |
| --- | --- |
| Country | Myanmar |
| Organization | Department of Basic Education No (2) |
| Position | Principal of Primary School |

| Title | Child-Center Approach |
| --- | --- |
| Period | April, 2012 to November, 2012 |
| Target Location | School Cluster |
| Target Group | Primary Teachers in School Cluster |
| NARRATIVE SUMMARY |  |
| < OVERALL GOAL > |  |
| Teachers in school cluster will be able to teach lessons with Child-Centered Approach |  |
| < SPECIFIC OBJECTIVES> (PROJECT PURPOSE) |  |
| Teachers can do Lesson Study |  |
| < YOUR LEARNING IN JAPAN> |  |
| 1.Japanese Textbooks 2.Japanese Mathematics Content for Elementary School 3.Child-Center Apporach 4.Developing 3 ways of Thinking 5.Lessory Study |  |
| < OUTPUTS by applying your learning in Japan> |  |
| Output 1 Output 1 Authorities from Township Education Office agree to Project implementation Output 2 Teachers in the same school can prepare the lessons together to become CCA Output 3 Teachers can conduct Lesson Study in School Cluster Output 4 Teachers can teach Mathematics to their students using child-centered Approach |  |
| < ACTIVITIES > |  |
| Output 1 Lesson Study system is developed Activity 1.1 Primary Principals from the school cluster prepare proposal for the authorities in Township Education Office - There are 5 teachers attend to the training workshop. - Students want do their presentations Output 2 Teachers in the same school can prepare the lessons together to become CCA Activity 2.1 Choose one lesson from the textbook Activity 2.2 Study it together with the aid of Teacher Guide developed by JICA-SCCA Project Activity 2.3 Prepare teaching aids Output 3 Teachers can conduct Lesson Study in School Cluster Activity 3.1 Demonstrate the prepared lesson Activity 3.2 Discuss and Learn among the teachers in the school cluster Activity 3.3 Improve the lesson Output 4 Teachers can teach Mathematics to their students using child-centered Approach Activity 4.1 Prepare the everyday lesson together in the school Activity 4.2 Daily teaching is observed by the Principal Activity 4.3 Feedback session is weekly conducted |  |

Plan of Operation

| Output No. | Activities | Expected results | Time Schedule |  | Persons in charge | Implementers | Materials, equipments | Budget | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output 1 Lesson Study system is developed | Activity 1.1 Assistant Lecturer prepares proposal for the principal authorities in Education Collage | Principal agree to conduct the Lesson Study in School Cluster | 05/01 to 05/ 21 | Primary Principals from the school cluster |  | Primary Principals from the school cluster | Letters | --- |  |
| Output 2 Teachers in the same school can prepare the lesson together to become CCA | Activity 2.1 Choose one lesson from the textbook | Collegial sprit (work together) | 06/01 to 0 6/ 07 | Primary Principal |  | Primary Principal | Text book Teacher Guide | -- |  |
|  | Activity 2.2 Study it together with the aid of Teacher Guide developed by JICA-SCCA Project | CCA based lesson | 06/ 01 to 06/07 | Primary Principal |  | Primary principal & teachers |  |  |  |
|  | Activity 2.3 Prepare teaching aids | Teachers will be able to prepare appropriate teaching aids | 06/08 to 06/14 | Primary Principal |  | Primary principal & teachers | -Paper -Scissors -Other necessary locally available materials | ---- |  |
| Output 3 Teachers can conduct Lesson Study in School Cluster | Activity 3.1 Demonstrate the prepared lesson | Handouts and power point on open ended approach | 06/15 to 06/21 | Cluster Head |  | Primary principals & Teachers | Venue Class Materials Students | --- |  |
|  | Activity 3.2 Discuss and Learn among the teachers in the school cluster | Teachers will be able to prepare teaching aids | 06/22 to 06/30 | Cluster Head |  | Primary principals & teachers | -- |  |  |
|  | Activity 3.3 Improve the lesson | Teachers will be able to improve the lesson | 06/22 to 06/30 | Cluster Head |  | Primary principals & teachers |  |  |  |
| Output 4 Teachers can teach Mathematics to their students using child-centered approach | Activity 4.1 Prepare the everyday lesson together in the school | Teachers will promote the working together spirit | 05/01 to 11/30 | Primary principal |  | Primary principal & teachers | Textbook Teacher Guides Reference books such as Pyin-nya- ta- zaung |  |  |
|  | Activity 4.2 Daily teaching is observed by the Principal | Principal will be able to observe the lesson | 07/01 to 11/30 | Primary principal |  | Primary principal & teachers |  |  |  |
|  | Activity 4.3 Feedback session is weekly conducted | Principal will be able to give appropriate feedback for the improvement of the lesson | 07/01 to 11/30 | Primary principal |  | Primary principal & teachers |  |  |  |